## Sheet1
Project Diary
Day | Month | Time Spent | Goals | Accomplished | Task Description
17th | October | 3h | Design research | Yes | Reseraching trending and according designs
23rd | October | 2h | Login research | Yes | Login and research efficient algorithms
30th | October | 3h | Login implementation | Yes | Implementing login and registration systems
12th | November | 2h | Website architecture | Yes | Researching website architecture
12th | November | 2h | Architecture implementation | Yes | Implementing researched architecture
8th | December | 1h | Design touch up | Yes | Design and front end implementation and touch up
14th | December | 1h | Researching jQuery | Yes | Reseraching jQuery algorithms
14th | December | 2h | Researching blogging system | Yes | Researching how blogs work and how they are implemented
17th | January | 3h | Blog templating | Yes | Creating a template for blog to see the up-coming design
23rd | January | 1h | Blog implementation | Yes | Implementing blog template using the templates created
4th | February | 2h | Symfony and Silex research | Yes | Research how to implement Silex framework
5th | February | 3h | Silex implementation | Yes | Implementing Silex framework
14th | February | 1h | Symfony implementation | NO | Implementing Symfony
23rd | February | 2h | Twig | 50% | Getting project ready for TWIG
27th | February | 2h | Security | NO | Research for security possibilities
1st | March | 1h | Styling | Yes | Styling front end
3rd | March | 4h | Web app stability | NO | Ensuring web app is stable and free of bugs and crashes
8th | March